## Sheet1
Category | Milestone | Effort (days) | Responsible | Notes
Mobile App | Android build | 3 | Both | Aim for end of next week to release to play store
Mobile App | Apple build | 3 | Both | Aim for end of next week to release to Apple store
Mobile App | MBI Lookup Capability | 3 | Both
Mobile App | Audit Log (observability) | 3 | Lyudmil | Aim for end of this week
Mobile App | UI/UX Improvements (icons, design, etc.) | 2 | Max | Check and critique from expo.dev
Mobile App | Native email sending | 2 | Lyudmil
Web App | Select Quote Capability | 2 | Max | Enroll in CMS and setup eligibility rules
Web App | Redesign | 5 | Both
Web App | Front facing interface for onboarding |  | Both
Web App | Billing module (batches) - design |  | Both
Web App | Billing module (batches) - business rules |  | Both
Backend | Billing module (batches) - backend |  | Lyudmil
Backend | Single-tenant migration | 0 | Lyudmil | Allows for resource flexibility per client size
Backend | Authentication | 4 | Lyudmil | Microsoft Entra ID - add passkey
Backend | Deployment Pipeline | 2 | Lyudmil | Aim for end of this weekend